## Subtask Template
Summary* | Description | Component ID* | Product ID* | Type of Work* | Planned Start* | Due Date* | Original Estimate* | Remaining Estimate* | Assignee | Reporter | Epic Link
[DD] [GET_DPMS] Create UC | [DD] [GET_DPMS] Create UC | 89486 | 3827093 | Create | 2025-10-01T09:00 | 2025-10-31 | 1m | 1m | thanhbc1 | tuantd23 | FHMPSATIB2JA-2595
[DD] [GET_DPMS] Review UC | [DD] [GET_DPMS] Review UC | 89486 | 3827093 | Review | 2025-10-01T09:00 | 2025-10-31 | 1m | 1m | thanhbc1 | tuantd23 | FHMPSATIB2JA-2595
[DD] [GET_DPMS] Update UC | [DD] [GET_DPMS] Update UC | 89486 | 3827093 | Correct | 2025-10-01T09:00 | 2025-10-31 | 1m | 1m | thanhbc1 | tuantd23 | FHMPSATIB2JA-2595
[DD] [HLR_HLAP] Create UC | [DD] [HLR_HLAP] Create UC | 89486 | 3827093 | Create | 2025-10-01T09:00 | 2025-10-31 | 1m | 1m | hainv21 | tuantd23 | FHMPSATIB2JA-2596
[DD] [HLR_HLAP] Review UC | [DD] [HLR_HLAP] Review UC | 89486 | 3827093 | Review | 2025-10-01T09:00 | 2025-10-31 | 1m | 1m | hainv21 | tuantd23 | FHMPSATIB2JA-2596
[DD] [HLR_HLAP] Update UC | [DD] [HLR_HLAP] Update UC | 89486 | 3827093 | Correct | 2025-10-01T09:00 | 2025-10-31 | 1m | 1m | hainv21 | tuantd23 | FHMPSATIB2JA-2596
[DD] [DOCU_EVENT_MSG] Create UC | [DD] [DOCU_EVENT_MSG] Create UC | 89486 | 3827093 | Create | 2025-10-01T09:00 | 2025-10-31 | 1m | 1m | anhnd49 | tuantd23 | FHMPSATIB2JA-2597
[DD] [DOCU_EVENT_MSG] Review UC | [DD] [DOCU_EVENT_MSG] Review UC | 89486 | 3827093 | Review | 2025-10-01T09:00 | 2025-10-31 | 1m | 1m | anhnd49 | tuantd23 | FHMPSATIB2JA-2597
[DD] [DOCU_EVENT_MSG] Update UC | [DD] [DOCU_EVENT_MSG] Update UC | 89486 | 3827093 | Correct | 2025-10-01T09:00 | 2025-10-31 | 1m | 1m | anhnd49 | tuantd23 | FHMPSATIB2JA-2597
Instructions:
- Fields marked with * are required
- Fill in Summary, Description, and Type of Work for each subtask
- Use Component IDs from the Components sheet
- Use Product IDs from the Products sheet
- Use Type of Work values from the Types of Work sheet
- Use format "YYYY-MM-DDTHH:mm" for Planned Start
- Use format "YYYY-MM-DD" for Due Date
- Time estimates: 8h, 2d, 1w 3d, etc.
- Assignee defaults to your username but can be changed
- Reporter defaults to your username but can be changed

## Components
Component ID | Component Name
95311 | <Track Name>
96772 | Common
97326 | CPMS
89486 | Detailed Design
89485 | Development
97931 | GATEGWMSGING
97325 | GCS
97324 | HCS
89460 | Horizontal Implementation
97872 | HORIZTPTGWREST
87454 | HT
95771 | HTCS
89626 | OASS
89568 | Others
89484 | Project Record
87455 | QC and Wharf
94542 | ROCS
87458 | ROMS
87457 | SOSS
97268 | SOSSGWMSGING
96912 | TJCS
87456 | Yard Ops
97318 | YardGWREST
97830 | YOS

## Products
Product ID | Product Name | Phase | Product Type | Version | Status | Final | Use for Productivity | Milestone | Is Deliverable | Unit | Actual Size | Planned Size | Actual Release | Planned Release | Re-planned Release | Re-planned Reason
3717401 | CM Record |  | CM Record |  | Open | Yes | No |  | No | Microsoft Word Page |  | 0,00 |  | 2026-04-30
3817879 | Detail Design | Detail Design | Detailed Design |  | Open | No | No | Release 1 - Design | Yes | Item |  | 600,00 |  | 2025-11-30
3717394 | Detail Design - Release 2 | Detail Design | Detailed Design |  | Cancelled | No | No | Release 2 - Design | No | Item |  | 800,00 |  | 2025-10-31
3827093 | Detailed Design |  | Detailed Design |  | Open | No | Yes |  | No | Microsoft Word Page |  | 0,00 |  | 2026-04-30
3883580 | Development | Coding | Source Code |  | Open | No | Yes |  | Yes | Java LOC |  | 0,00 |  | 2026-04-30
4500599 | FT Report |  | Unit Test Report |  | Open | No | Yes |  | No | Test Script |  | 0,00 |  | 2026-04-30
4500585 | FT Spec |  | Unit Test Case |  | Open | No | Yes |  | No | Test Script |  | 0,00 |  | 2026-04-30
3717400 | Project Record |  | Project Record |  | Open | Yes | No |  | No | Microsoft Excel Sheet |  | 0,00 |  | 2026-04-30
3717402 | QA Record |  | QA Record |  | Open | Yes | No |  | No | Microsoft Excel Sheet |  | 0,00 |  | 2026-04-30
3746462 | Requirement |  | URD |  | Open | Yes | No |  | No | Microsoft Word Page |  | 0,00 |  | 2026-04-30
3936994 | Training Record |  | Training Record |  | Open | No | No |  | No | Slide |  | 0,00 |  | 2026-04-30
4495757 | UT Report |  | Unit Test Report |  | Open | No | Yes |  | No | Test Script |  | 0,00 |  | 2026-04-30
4495755 | UT Spec |  | Unit Test Case |  | Open | No | Yes |  | No | Test Script |  | 0,00 |  | 2026-04-30

## Types of Work
Type ID | Type Name
Create | Create
Study | Study
Review | Review
Correct | Correct
Translate | Translate